## Summary
Sharwa – Create New Store (Tenant Onboarding): Next.js ↔ Django gap analysis
Analysis date: 2026-10-21. No code written yet; implementation waits on the two open decisions (see Decisions tab).
Discrepancies by severity | Count
Blocker | 2
High | 2
Medium | 3
Low | 2
Total | 9
Status | Count
Planned | 7
Needs decision | 2
Decisions still unanswered | 2
Tabs: Discrepancies · Endpoints · Plan · Decisions. Yellow cells on the Decisions tab are for your answers.

## Discrepancies
Discrepancies between the Next.js wizard and Django
Severity and Status are drop-downs. Severity is my assessment: Blocker = flow cannot run with mocks off or is unsafe; High = wrong behaviour or security gap; Medium = user-visible mismatch; Low = cosmetic or self-correcting.
# | Area | Severity | Next.js wizard expects | Django today | Impact | Planned fix | Status
1 | No JSON API | Blocker | 3 JSON endpoints (register, verify-otp, resend-otp) + market categories; pending signup identified by otp_token | HTML pages only (POST /register/, /register/verify-otp/); pending signup kept in the browser session; no resend at all | Wizard cannot run against Django with mocks off | Add 4 public endpoints in api/; pending signup + hashed code in Redis keyed by a random otp_token | Planned
2 | Subdomain length | Medium | 3–63 characters (SUBDOMAIN_MIN/MAX in src/lib/tenant.ts) | Max 50 (TenantRegistrationForm), no minimum | A 51–63 character name passes the live check, then fails at submit with an unexpected message | One rule in tenants/validators.py used everywhere; recommended 3–50 (frontend SUBDOMAIN_MAX → 50) | Needs decision
3 | Phone format | Medium | Only 967/966 + 9 digits after normalizePhone | Anything clean_phone_number returns | Backend could create stores with numbers the frontend would never send | API enforces the frontend rule ^(967¦966)\d{9}$; HTML form unchanged | Planned
4 | "Number already has a store" message | Low | Shows the merchant-login link only if the message is exactly «هذا الرقم مرتبط بمتجر» | «رقم الواتساب هذا مسجل مسبقاً لدى متجر آخر. يُسمح بمتجر واحد لكل رقم.» | Login link never appears | API returns the frontend's exact text | Planned
5 | Duplicates found at code-check time | Medium | Field errors on merchant_phone / subdomain so the wizard returns to that field | One generic page error | Merchant lands on a dead end instead of the field to fix | verify-otp re-checks uniqueness and returns {field: [msg]} | Planned
6 | Rate limits | High | Reads 429 + Retry-After | Limits stored in the browser session | A script that sends no cookies skips the limits | Count per IP and per phone in Redis, with Django's existing numbers | Planned
7 | Store link after setup | High | Redirects to dashboard_url from the status endpoint | URL built from the calling host = localhost:8000 (internal host in production) | Merchant sent to Django's port instead of the Next.js dashboard | Status endpoint uses the original host/protocol the BFF forwards (X-Forwarded-Host/Proto) | Planned
8 | Code lifetime and lockout | Low | Mock: 5 min, 5 wrong attempts → 60 s lock; reads ttl_seconds and Retry-After | 10 min; 3 wrong attempts per 10 min per phone | None: the wizard adapts to the server's values | Keep Django's rules; return ttl_seconds = 600 and Retry-After | Planned
9 | Setting the first password | Blocker | {password, password_confirm} only | Sends a WhatsApp code to the store's number before the first password | As-is, anyone who opens a new store before its owner could claim it; flow can't run end-to-end with mocks off | Recommended: short-lived signed setup token on the dashboard link, required by set-password | Needs decision

## Endpoints
Endpoints: what each side has today
Step | Next.js expects | Django today | State
Store details | POST /api/v1/public/register/ {store_name, merchant_phone, subdomain, interested_categories[], agree_terms} → {otp_token, ttl_seconds, masked_phone} / 400 {field: [msg]} | HTML POST /register/ (session) | To build
Code check | POST /api/v1/public/register/verify-otp/ {otp_token, code} → {status_token, status_url} / 400 / 410 / 429 | HTML POST /register/verify-otp/ (session) | To build
Resend code | POST /api/v1/public/register/resend-otp/ {otp_token} → {ttl_seconds} / 429 + Retry-After | Does not exist | To build
Business categories | GET /api/v1/public/market-categories/ → [{id, name}] (active, by display_order) | Checkboxes in register.html only | To build
Subdomain check | GET /register/check-subdomain/?subdomain= → {available, reason} | Exists | Ready
Setup status | GET /register/status/<token>/ → {status, store_url?, dashboard_url?} | Exists (URLs need the host fix, item 7) | Fix needed
First password | POST /api/v1/auth/merchant/setup-password/ {password, password_confirm} | HTML setup_admin_password with WhatsApp code | Needs decision
Client model fields the wizard must supply
Django field | Wizard field | Required | Rule
schema_name | subdomain | Yes | Lower-case letters and digits; not reserved; unique
name | store_name | Yes | 3–100 chars; Django also rejects a duplicate name (case-insensitive)
merchant_phone | merchant_phone | Yes (unique) | Normalised, e.g. 967770841802
terms_accepted_at | agree_terms = true | Set at creation | Timestamp written when the store is created
interested_categories (M2M) | interested_categories[] | No | Active MarketCategory IDs
provisioning_status | — | Set by server | pending → provisioning → ready / failed (Celery)
Domain (primary) | — | Set by server | <subdomain>.<TENANT_BASE_DOMAIN>

## Plan
Implementation plan
# | Work item | Where | Notes | Fixes discrepancy #
1 | Shared signup code | tenants/views.py → shared function | HTML form and API create stores identically | 1, 5
2 | Public signup API | api/ (new views + urls) | Register, verify, resend, market categories; platform host only | 1, 3, 4, 5, 8
3 | Rate limits per IP and phone | api/ + Redis cache | Django's existing numbers | 6
4 | Store link host fix | tenants/provisioning.py | Use forwarded host/protocol from the BFF | 7
5 | Subdomain length rule | tenants/validators.py, src/lib/tenant.ts | Depends on Decision 1 | 2
6 | First password with setup token | api/views_auth.py, setup-password BFF + form | Depends on Decision 2 | 9
7 | Tests | api/test_onboarding_api.py | Same style as the auth tests | All
Note: store setup runs in Celery. Without a worker running, new stores stay "pending".

## Decisions
Open decisions
Fill in the yellow cells (column E) with your choice.
# | Decision | Recommendation | Alternative | Your answer
1 | Subdomain length | 3–50 characters everywhere (Django validator + frontend SUBDOMAIN_MAX) | Keep 63 (DNS label / schema limit) and raise Django's limit
2 | First password (item 9) | Include now: signed short-lived setup token on the dashboard link, required by set-password (one extra field in the frontend contract) | Separate task later; mocks must stay on for the full flow until then